## MonthlyProjectStatus
PRJ-3997-OEG_ADM_Agile_DevOps_Lab_Monthly Status Report - March 2016
Project Details
Project ID | PRJ-3997
Project Name | OEG_ADM_Agile DevOps Lab
Project Type | Development
Project Manager | RAVICHANDRAN MUTHU
Offerings / Unit | Agile DevOps Service Offering / ADM
Offering Owner | Prasad Surkund
Project Start Date | 2015-03-10
Project End Date | 2016-06-30
Tech Finance ID | 95806
Project Description
Setup an Agile DevOps Lab for client showcasing & walkthroughs; Agile CoE work; Execute Internal PoC's and Projects using Hexa Agile Frameworks, Models & Methodologies.
Key Achievements and Challenges in the Last Month
Accomplished: Prototype of HexaView Dashboard done with Kibana HexaView requirements were given and we found Kibana Dashboards would not suffice BI Tools are being analyzed right from Gartner Reports till Evaluation Editions Dream Delivery Initiative: Two out of Four applications of DL are analyzed for feasibility Jira and nCover Support Licenses renewed. SQL Compare Support license renewal need under analysis Challenges: BI Skill and Architect Skill lacking in current team to build a major product
Training Needs | Agile Training for Ram, new Consultant
Critical Risks | None
Critical Issues | None
Open RR's | None
Review by Competency | Weekly Review by Service Offering Owner
PHI | Not done yet
Open NC / Observations of IQA | No Audits done
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalizing BI Tool for HexaView |  |  |  |  | 2016-06-15 | 2016-06-15 | In Progress
Getting BI and Architect Consultants on board for HexaView |  |  |  |  | 2016-06-15 | 2016-06-15 | Complete
Kibana Dashboard to cover data from all Demo Tools |  |  |  |  | 2016-05-31 | 2016-05-15 | Abandoned
Plan for Single Click Framework Deployment |  |  |  |  | 2016-07-15 |  | On Hold
Plan for APIs to call Framework |  |  |  |  | 2016-07-15 |  | On Hold
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 0
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | None |  | Number of post shipment defects
|  |  | Severity | 0 | 0 | 0 | 0
Software / Hardware Licensing
Software / Hardware Requested |  | None availed this month
Software / Hardware Availed |  | None availed this month

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Ravichandran Muthu | PM | G8 | 50% | 2015-03-23 | 2016-06-30 | ADM
Vivek Gole | TM | G5 | 100% | 2015-03-27 | 2016-06-30 | ADM
Reena Elizabeth P | TM | G5 | 100% | 2015-04-17 | 2016-06-30 | ADM
Rama Chandran V | TM | G4 | 100% | 2016-04-18 | 2016-06-30 | ADM

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 0 | 0%
G3 | 6 | G3 | 0 | 0%
G5 | 1 | G4 | 1 | 25%
G6 | 2 | G5 | 2 | 50%
G7 | 1 | G6 | 0 | 0%
G8 | 2 | G7 | 0 | 0%
G4 | 3 | G8 | 1 | 25%
Grand Total | 16 | >G8 |  | 0%