## MonthlyProjectStatus
Akiva Status Report - May 2016
Project Details
Project ID | PRJ-4352 - HR-IT Take-Akiva - 92516
Project Name | [PRJ-4352]OEG_ES_PS_Akiva
Project Type | Maintenance
Project Manager | Krishna Patel
Offerings / Unit | OEG
Offering Owner | Venkataraman A r
Project Start Date | 2015-09-21
Project End Date | 2016-12-31
Tech Finance ID | 92516
Project Description
PGE: Requirement is to make Akiva compatible with 12c container pluggable DB. This requires to upgrade akiva compatible with Java version 1.5 to 1.8 . Post the upgrade implement akiva in PGE for FSCM and then for HCM. Columbia: Enhance Akiva to support kerberos single sign on.- ONHOLD Ascension Health: Requirement is to install akiva for FSCM and HCM. So questionnair has been sent , waiting for Vimal.
Key Achievements and Challenges in the Last Month
PGE : Accomplished: Installer with the configuration and setup documents are provided to PGE on 15th April. Waiting for PGE to complete implementation. Upgraded TOMCAT 5.5 to 6 and made it compatible with Java 1.5 to Java 1.8, Verified and upgraded all the libraries and classes which need to be packaged, Certified all the PL/SQL on oracle 12c container pluggable DB, Trouble shooted and conducted RCA for all the errors which came across during the course of upgrade, Upgraded spring 2.5 to Spring 4 ,Configuration and setup completed, Packaging is completed for FSCM , Packaging completed for HRMS, prepared installation , configuration documents and uploaded the code in to GIT. Waiting for PGE team to install akiva and let us know if there is any issues. Configured Log File Path i.e /psoft/AKIVA_LOGS for Akiva finance and Hrms in same root folder. Sometimes we not able to connect the DB. Work in progress: working on changing the log path. we need DBA's help as we can’t do it on our own as other instances also installed in this VM machine[172.25.164.205]. The following error we are getting in the Akiva.log "ORA-01652: unable to extend temp segment by 16 in tablespace PSTEMP" We need to change the log file path or increase the size. So working with DBA and system admin on the same. Ascension Health: Questionnair has been prepared and sent , waiting for Vimal.
Project Execution
Training Needs | Team requires kerberos training from Columbia | <mention the pending needs and challenges if any>
Critical Risks |  | <Refer critical risks from PP>
Critical Issues | 0 | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Complete akiva packaging FSCM Akiva |  |  |  |  | 30/04/2016 | 30/04/2016 | Completed
Complete akiva packaging HCM Akiva |  |  |  |  | 30/04/2016 | 20/04/2016 | Completed
Implement at PGE |  |  |  |  | 15/06/2016 | 15/06/2016 | Yet to Start
Implement at VIACOM |  |  |  |  | 15/4/2016 | 2016-12-04 | Completed
Implement Kerberos enabled Akiva for Columbia |  |  |  |  | TBD | TBD | Onhold
Fixing issues at viavom |  |  |  |  | 30/4/2016 | 30/4/2016 | Completed
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track(15 DAYS AHEAD of scheduled due date) |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | 1 |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | VM WARE WINDOWS 12 SERVERS 172.25.164.168, 172.25.100.72, 172.25.164.205,10.1.55.196

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Abdul aleem shaik |  | G3 | 100
veera vijay |  | G4 | 50
Mrinal kumar |  | G2 | 100
Krishna kishore patel |  | G7 | 50

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 25%
G3 | 1 | G3 | 1 | 25%
G7 | 1 | G4 | 1 | 25%
G4 | 1 | G5 | 0 | 0%
Grand Total | 4 | G6 | 0 | 0%
|  | G7 | 1 | 25%
|  | G8 | 0 | 0%
|  | >G8 |  | 0%