## MonthlyProjectStatus
CRES Offering Status Report -May 2016
Project Details
Project ID | PRJ-4660 - OEG_BFS_CRES Works
Project Name | CRES Offering
Project Type | Development
Project Manager | Santhakumar
Offerings / Unit | Workspace Utilization
Offering Owner | Alok Mishra
Project Start Date | 2016-03-10
Project End Date | 2016-09-30
Tech Finance ID | 92524
Project Description
CRES Service Offering is a solution to measure the utilization of seats, meeting room, board room facilities, Lease, Rent and Engery Utilization in percentage and actual currency 1) Accurately captures the seats utilised BU/floor/duilding/site/location/country/region wise. 1) Accurately captures the Lease, Rent and Engery utilised in BU/floor/duilding/site/location/country/region wise. 2) Utilization of seats can be compared with the previous period. 3) User level access screen like Executive and Admin Dashboard.
Key Achievements and Challenges in the Last Month
Accomplished: Lease and Rental Payment Module: 1. Creation of Dashbaord to capture rental and Lease payment details by floor, building, City and Region against Market Price - Completed Energy Consumption Module: 2.Creation of Dashbaord to capture Actual Energy consumption details by floor, building, City and Region wise against Budgeted Energy Consumption - Completed Challenges: NA
Project Execution
Training Needs | Not Needed | <mention the pending needs and challenges if any> No pending task
Critical Risks | No risk | <Refer critical risks from PP> No Risk
Critical Issues | No Risk | <Refer critical issues from PP / WSR> No Risk
Open RR's
Review by Competency - completed on 31-5-2016 | <Review conducted in reporting period> | <Plan for next month> Big Data Integration, Facility Management Dashboard
PHI is 91.5 | Target <100>, Actuals <91.5>
Open NC / Observations of IQA : No Open NC | 0
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
lease and Rental payment module development - 1. Creation of Dashbaord to capture rental and Lease payment details by floor, building, City and Region against Market Price |  |  |  |  | 31/05/2016 | 31/05/2016 | Completed
Lease and Rental payment module development CHANGES - Sprint changes incorporated |  |  |  |  | 31/05/2016 | 31/05/2016 | Completed
Energy Consumption module development Actual Energy consumes vs Budget energy Consumption |  |  |  |  | 31/05/2016 | 31/05/2016 | Completed
Project Health Card |  |  | Metrics
Schedule | The Project schedule is extended |  | Schedule Variance |  | 0%
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | No risk |  | Consultant Utilization % |  | 100
Issues | No issues |  | Number of post shipment defects
|  |  | Severity : none | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Tableau Desktop and Server Environment was purchased
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Santhakumar | PM | G5 | 100 | 10th March 2016 | 2016-09-01 | BFS
Sivaranjan | Developer | G5 | 100 | 10th March 2016 | 2016-09-01 | BFS

## Pivot
Row Labels | Grade | No. of consultant | % of Total FTE
G5 | G2 | 0 | 0%
Grand Total | G3 | 0 | 0%
| G4 | 0 | 0%
| G5 | 2 | 100%
| G6 | 0 | 0%
| G7 | 0 | 0%
| G8 | 0 | 0%
| >G8 |  | 0%