## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4713
Project Name | Equity Research Offering
Project Type | Development
Project Manager | Indumathy Kannan
Offerings / Unit | Equity Research Offering
Offering Owner | Pramit Joshi
Project Start Date | 2016-03-10
Project End Date | 2016-05-31
Tech Finance ID | 92526
Project Description
"Equity Research Offering is a solution to build and maintain ""Digital Equity Research"" on the Big Data Platform with the below features 1) Significantly reduces the time and energy of Equity Researcher in terms of collating news from various sources, aggregate structured (Financial Metrics) and Unstructured (Press Releases / Announcements) 2) Store in a central place and Process the information as required 3) Information Delivery mechanism to analyze the metrics and trends via Dashboards, and provide inputs to the equity research report"
Key Achievements and Challenges in the Last Month
Accomplished: 10-K Report Display - 5/4/2016 - Completed Populating Modelling input sheet for P/E multiple - 5/4/2016 - Completed Macro for P/E multiple - 5/9/2016 - Completed Integrating P/E multiple with ER Framework(Dashboard) - 5/13/2016 - Completed Final Version of the Analyst Report - 5/18/2016 - Completed US DMZ configuration - 5/20/2016 - Completed Financial modelling integration - PE - 5/25/2016 - Completed IPAD deck Preparation for Sales Team - 5/20/2016 - Completed IPAD upgradation for sales meet - 5/20/2016- Completed Final Report Enhancements (Corrections)- Audit Trailing in Analyst Report - WIP P/E multiple model (Macro Enhancements) - WIP Twitter Analytics - WIP Challenges: Integration of DCF Model with ER framework
Project Execution
Training Needs | None | <mention the pending needs and challenges if any>
Critical Risks | None | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | None
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Planned in June
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Modification in Final report for demo (Corrections) |  |  |  |  | 2016-06-07 | 2016-06-07 | WIP
Modification in P/E multiple (Enhancements) |  |  |  |  | 2016-06-07 | 2016-06-07 | WIP
Mobile dashboard changes |  |  |  |  | 2016-06-18 | 2016-06-18 | WIP
Twitter Sentiment analysis integration |  |  |  |  | 2016-07-01 | 2016-07-01 | WIP
Financial modelling integration - DCF |  |  |  |  | 2016-06-24 | 2016-06-24 | WIP
Audit Trailing of Analyst report |  |  |  |  | 2016-06-17 | 2016-06-17 | WIP
Audit Trailing of Modelling |  |  |  |  | 2016-06-17 | 2016-06-17 | WIP
Macro News - Web Scraping, Loading and Dashboard |  |  |  |  | 2016-07-08 | 2016-07-08 | Yet to Start
News in Real Time |  |  |  |  | 2016-07-15 | 2016-07-15 | Yet to Start
Google Alerts integration |  |  |  |  | 2016-07-15 | 2016-07-15 | Yet to Start
Xurmo integration (Complexity is yet to be ascertained) |  |  |  |  | 2016-07-31 | 2016-07-31 | Yet to Start
Tweaking of iPad dashboards |  |  |  |  | 2016-07-31 | 2016-07-31 | Yet to Start
Full set of Documents, Final Sign off, Handing Over Procedure to Innovation Lab |  |  |  |  | 2016-08-15 | 2016-08-15 | Yet to Start
Estimate Model |  |  |  |  | 2016-08-15 | 2016-08-15 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 0
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | No Issues Identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Bakkiya Lakshmi | Developer | G2 | 100 | 2016-03-10 | 2016-07-31 | BFS | Release date may change based client specific demo / changes ad-hoc
Indumathy K | PM | G4 | 100 | 2016-03-10 | 2016-07-31 | BFS | Release date may change based client specific demo / changes ad-hoc
Shaik Akram Basha | Developer | G4 | 100 | 2016-03-10 | 2016-08-15 | BFS | Release date may change based client specific demo / changes ad-hoc
Jyothi Swaroop Mummidi | BA | Trainee | 100 | 2016-03-10 | 2016-07-01 | BFS | Release date may change based client specific demo / changes ad-hoc

## Pivot
Grade | No. of consultant | % of Total FTE
G2 | 2 | 50%
G3 | 0 | 0%
G4 | 2 | 50%
G5 | 0 | 0%
G6 | 0 | 0%
G7 | 0 | 0%
G8 | 0 | 0%
>G8 |  | 0%