## -Context+
Context +- Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | Resume Analytics
Project Type | Development
Project Manager | Vipul Gupta
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Context + is a text mining offering 1) Resume Analytics - To match the profile with the corresponding job description and rank them based on skill set, location, years of experience and other entity extracted from the profile. 2) Store in a central place and Process the information as required 3) Vector space model algorithm is used to rank the profiles.
Key Achievements and Challenges in the Last Month
Accomplished: Entity Extraction, Completed Extracted candidates experience from the profiles by handling all possible date formats and integrated python and java UI using Rest API Challenges faced: Algorithm, Completed Have preprocessed(filtered) the Resumes based on all the business rules and We got some issues in Ranking priority based on skills and its corresponding experience which is in progress Challenges: Ranking Prioritization based on the Business rules. Pre-Processing of the resumes. Handling multiple date formats(ex:02.02.2016 ,02 feb 16,02 feburary 2016 etc….) Integration issue got solved by encoding format
Project Execution
Training Needs | Solr - self study
Critical Risks | none | <Refer critical risks from PP>
Critical Issues | none | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Entity extraction and taxonomy building |  |  |  |  | 2016-02-05 | 16/5/16 | Completed
Profile matching based on business rules |  |  |  |  | 16/5/16 | 23/5/2016 | Completed
Prioritization based on the business rules | [6 empty] | Completed
UI Development |  |  |  |  | TBD | TBD
Testing and corrections |  |  |  |  | TBD | TBD | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | So far no issues identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## MMA
MMA Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Vipul Gupta
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Image Analytics is a offering 1) Detect factures in X-Ray images and to locate the facture area. 2) Object identification and to check the quality of the object in that image.
Key Achievements and Challenges in the Last Month
Accomplished: 1) Installing using pre-build libraries. Completed 2) Installing from the source. Completed 3) developed a code for face detection using OpenCV JAVA Completed 4) working on with connecting Visual Recognition API using Python.(WIP) 5) working on with connecting Visual Recognition API with Nodejs.(WIP) Challenges: Tried installing in Windows but faced lot of problems. After we proceeded installing in Ubuntu. It was successfully installed and we were able to build all the libraries without any error.
Project Execution
Training Needs | Open CV, Cognitive offering from MS, Google
Critical Risks | none | <Refer critical risks from PP>
Critical Issues | none | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Opencv installation on Windows |  |  |  |  | 20/5/2016 | 24/5/2016 | Not completed and the installation givers errors
Opencv installation in Ubuntu |  |  |  |  | 20/5/2016 | 24/5/2016 | Completed
Installing the binaries for opencv in ubuntu |  |  |  |  | 27/5/2016 | 30/5/2016 | Completed
Testing with the libraries |  |  |  |  | TBD | TBD | WIP
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | So far no issues identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## Governance Dashboard
Governance Dashboard Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | Governance Dashboard
Project Type | Development
Project Manager | Vipul Gupta
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-10
Project End Date | 2016-12-01
Tech Finance ID | 92514
Project Description
Governace Dashboard 1) It will allow the users to monitor the activity in the cluster such as jobs, data load etc.. 2) Data Growth monitoring 3) Data Usage monitoring
Key Achievements and Challenges in the Last Month
Accomplished: 1.Explored Chart.js from google and github(shiva) Completed 2.Had a glimpse from the samples of Chart.js(shiva and Shashi) Completed 3.Started creating login page for the Governance Dashboard(Shashi) Completed 4.Try to create first chart using Chart.js(Shiva) Completed 5. Created table in MySql for the users to integrate it with the login page.(Shashi) Completed 6.Exploring HTML to have tidy web page(Shiva) Completed Challenges: Extraction of the metrics for governance
Project Execution
Training Needs | Self Study- Plotly/D3.js/substitute system | <mention the pending needs and challenges if any>
Critical Risks | none | <Refer critical risks from PP>
Critical Issues | none | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Dashboard development using Chart.js |  |  |  |  | 2016-05-30 | 2016-06-10 | In progress
Implementation in Java Script - for charts developed using chart.js |  |  |  |  | TBD | TBD | WIP
Creation of Login page |  |  |  |  | TBD | TBD | WIP
Exploring the metrics and architecture of Cloudera Navigator and Apache Falcon |  |  |  |  | TBD | TBD | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | So far no issues identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## Dr. Hadoop
Dr. Hadoop Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Vipul Gupta
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Dr.Hadoop is a Tool 1) It will analys the customers existing system and recommend hadoop system for the user 2) Auto deployement of the hadoop cluster
Key Achievements and Challenges in the Last Month
Accomplished: 1) Landing page in for Dr,Hadoop to get the users basic information. (Completed) I. Design web page with HTML II. Adding styles with CSS III. Validate the web page with Java script. 2) Store the data in the Data Base (Completed) i. Create the tables in the database ii. Connect the web page and the database. iii. Store the input data from the web page and store it in the DB 3) Create a web page that contains the Questionnaires (Completed)
Project Execution
Training Needs | Training for Java/.Net | <mention the pending needs and challenges if any>
Critical Risks | none | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Calculation for sizing |  |  |  |  | TBD | TBD | Completed
UI Development |  |  |  |  | TBD | 2016-06-11 | WIP
Scripts Generation( Auto Deployment of Hadoop clusters) |  |  |  |  | TBD | 2016-06-18 | WIP
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | So far no issues identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## Big Connect
Big Connect Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | BIBA - Soultion - Bigleap
Project Type | Development
Project Manager | Vipul Gupta
Offerings / Unit | OEG
Offering Owner | Ranga
Project Start Date | 2016-02-01
Project End Date | 2016-12-31
Tech Finance ID
Project Description
Soltution for Metadata management and migration automation for various report and ETL tools. BIMA, DIMA, DART, INFAGEN, SQL PARSER, RLA , SLA, FIRE helps variours customer to capture metadata and doing automation of impact analysis & migraions.
Key Achievements and Challenges in the Last Month
Accomplished: 1. Create login screen and login functionality with session management and clearing session using logout Completed a. Wrote CSS for UI and Java Script for client side validation b. Creating a table to store user's credentials c. Check the user input from the HTML page and redirect the use to the next page or provide some messages for their inputs d. Storing the valid username in session e. Created logout process to terminate session which create by the valid user 2. Creating UI for getting RDBMS details (source Details) Completed a. Wrote CSS for UI and Java Script for client side validation b. Check user input from HTML page and redirect the use to the next page or provide some error messages for their inputs
Project Execution
Training Needs | none | <mention the pending needs and challenges if any>
Critical Risks | none | <Refer critical risks from PP>
Critical Issues | none | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
identify DB2 instance |  |  |  |  | 2016-06-16 | 2016-06-16 | WIP
identify DB2 datatypes and hive mapping |  |  |  |  | 2016-06-10 | 2016-06-10 | WIP
generating sqoop scripts |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
testing generated sqoop scripts |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | So far no issues identified |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | Hardware: 64 Bit Cloud servers Softwares: Eclipse, JDK 1.7, MySQL 5.7, HDP 2.2

## ConsultantMatrix (hidden)
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G2
G2
G2

## Pivot (hidden)
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 3 | 75%
G3 | 6 | G3 | 1 | 25%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16