## MonthlyProjectStatus
DMO- May 2016
Project Details
Project ID | 4327
Project Name | Data Modernization Offering
Project Type | Development
Project Manager | Senthil Kumar k
Offerings / Unit | OEG
Offering Owner | Prasad Karkhanis
Project Start Date | 2016-03-10
Project End Date | 2017-12-31
Tech Finance ID | 91530
Project Description
Data Modernization solution provides automated way to migrate the data from point A to point B by making use of various solution components like HexaRule, DIMA Plus, Automaton, Data Recon etc. The tool helps organization to reduce the cost of delivery by automation and provides extreme flexibility to business users in handling the business rule at enforcing them into data validation process with minimal efforts
Key Achievements and Challenges in the Last Month
.net Accomplished: Training Manual and Instruction Manual for each Module similar to Infagena and Automaton - Completed Profiler: Including record count in Code Management Option - Completed Automaton (Release 2.2): load excel to be renamed as Data Management in Automaton with option of upload and Download - Completed Define Parameter Value - Completed Data upload utility to support multiple file types - Completed Data Type Template - Completed Hexarule (Release 2.2): Execution of HaxaRule process in Offline Mode - Completed DATARECON: Master Setup: Audit Process -Orchestration UI - Completed Audit Process -Workflow - Completed Process Orchestration -UI Chang - Completed Java Bug Fixes in Hexarule - In progress Home Page and Integration - In progress Hexarule documentation POCs in Progress Xerox - In progress ICMA - Inprogress UCS Leasing - Completed Balayse - Inprogress Challenges: SSIS .Net skilled person to replace suganya Java Skilled profile to Replace Naga Kisore.
Project Execution
Training Needs | Windows work flow foundation
Open RR's | Open Requirement for SSIS Replacement profile, Java replacement profile - ASAP
PHI | Actual:87
Project MileStones |  |  |  | Target Date | Expected Completion Date | Status
Hexarule -Release 2.2 |  |  |  | 2016-05-31 | 2016-05-31 | Completed
Automaton-Release -2.2 |  |  |  | 2016-05-31 | 2016-05-31 | Completed
POC |  |  |  | 2016-05-31 | 2016-05-31 | In progress
Java Hexarule |  |  |  | 2016-05-31 | 2016-05-31 | Completed
Project Health Card |  | Metrics
Schedule | On Track | Schedule Variance |  | 0%
Resourcing | Awaiting for Replacement profile | Effort Utilization % |  | 100%
Risks | Replacement for Suganya (SSIS) , Naga (Java) | Consultant Utilization % |  | 100%
Issues |  | Number of post shipment defects
|  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Gopinath P | Database Develper | G5 | 100 | 2016-02-15 |  | BI
MuthuMani R | Module Lead .net | G5 | 100 | 2015-11-16 |  | BI
Nanthakumar thangavel | .net Developer | G5 | 100 | 2015-12-01 |  | BI
Rahul Mohanan | Report Developer | G2 | 100 | 2015-11-16 |  | BI
Sathya Murthy vis | Java Developer | G6 | 100 |  |  | BI | Released
Suganya | SSIS - Architect | G6 | 100 | 2016-02-12 |  | BI
Suresh balusamy | .net Developer | G3 | 100 | 2016-01-01 |  | BI
Venkateshwaralu | Java Developer | G3 | 100 | 2016-01-01 | 2016-05-31 | BI | Released
Vishaka Deokar | .SSIS Pentaho Develper | G2 | 100 | 2016-04-01 |  | BI
Senthil kumar k | Project Manager | G7 | 100 | 2016-05-16 |  | BI | Replacement
Muthuvel | Java Developer | G5 | 0 | 2016-06-01 |  | BI | Replacement
Anand | Oracle Developer | G3 | 100 |  | 2016-05-31 | BI | Released
Naga kishore | Java Developer | G4 | 100 | 2016-04-06 |  | BI | To be released, Waiting for replacement profile
Justin | Project Manager | G7 | 100 | 2016-01-01 | 2016-05-31 | BI | Released
Sravana Kumari | Sr Software engineer | G3 | 0 | 2016-06-06 |  |  | Replacement
Gopal Nayak | Developer | G5 | 100 |  | 2016-05-13 |  | Released

## Pivot
Grade | No. of consultant | % of Total FTE
G2 | 2 | 15.38%
G3 | 3 | 23.08%
G4 | 1 | 7.692%
G5 | 4 | 30.77%
G6 | 1 | 7.692%
G7 | 2 | 15.38%
G8 | 0 | 0%
>G8 |  | 0%