## MonthlyProjectStatus
OEG_ES_CloudMorphy Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4353
Project Name | OEG_ES_CloudMorphy
Project Type | Maintenance
Project Manager | krishna kishore patel
Offerings / Unit | Innovation Lab
Offering Owner | Venkataraman A r
Project Start Date | 2016-05-01
Project End Date
Tech Finance ID | 92516
Project Description
‘CloudMorphy’ is Hexaware’s IP Accelerator for migrating enterprise applications to Cloud-based / On-premise enterprise applications. It has been successfully used in several Fusion implementation projects and tested across Fusion, Workday, PeopleSoft and SAP. The current sales model of ‘CloudMorphy’ has hit a roadblock with customers demanding a shift to an as-a-service model. Customers no longer want to buy software – instead, they are demanding a hosted or cloud service. This project is a feasibility study about moving the .NET based ‘CloudMorphy’ tool from an On-premise / license model to a SaaS model.
Key Achievements and Challenges in the Last Month
Accomplished: Latest Source Code moved to GIT HUB; Acquired Cloudserver for CloudMorphy SQLServer DB; Acquired Instances for CloudMorphy demo with PeopleSoft, SAP, Workday and Fusion; MS Azure training to CloudMorphy team; SaaS feasibility study document ready Cloud testing of cloudmorphy in Azure VM.- Completed Cloud morphy presentation and Demo to data team - Completed Challenges: Availability of knowledgeable Functional resources for end-to-end operation for Fusion, SAP and Workday.C Complexity in deploying cloudmorphy in Azure . Conflicts with SQL Azure compared with local SQL server . Work in progress: Waiting for Azure architect for fixing the SQL conflicts in Azure and find an alternate solution to deploy the application in remote desktop .
Project Execution
Training Needs | <any training pending> | Team has undergone MS Azure Training
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's | 59443 | Withheld because of cancellation of project CM Successfactors
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Shared SaaSification feasibility study report with Venkataraman A R | [5 empty] | 6th April 2016 | Awaiting response
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | 2 |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | CloudServer 4 Core, 8 GB RAM, C Drive 50 GB and D Drive 50 GB with Windows Server 2012 STD, IIS, MSSQLServer
Software / Hardware Availed |  | CloudServer 4 Core, 8 GB RAM, C Drive 50 GB and D Drive 50 GB with Windows Server 2012 STD, IIS, MSSQLServer

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
krishna kishore patel | PM | G7 | 50 |  |  | MS
Vignesh muthiah Chidambaram | .NET Architect | G4 | 100 |  |  | DCCRM

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G7 | 1 | G2 |  | 0%
G4 | 1 | G3 |  | 0%
Grand Total | 2 | G4 | 1 | 50%
|  | G5 |  | 0%
|  | G6 |  | 0%
|  | G7 | 1 | 50%
|  | G8 |  | 0%
|  | >G8 |  | 0%