## MonthlyProjectStatus
PRJ-4693-OEG_ADM_AM_HEXJAVA_SWFACTORY_Monthly Status Report - April 2016
Project Details
Project ID | PRJ-4693
Project Name | OEG_ADM_AM_HEXJAVA_SWFACTORY
Project Type | Development
Project Manager | RAVICHANDRAN MUTHU
Offerings / Unit | Application Modernization / ADM
Offering Owner | Santhosh Kumar Ramabadhran
Project Start Date | 2016-03-15
Project End Date | 2016-06-03
Tech Finance ID | 92502
Project Description
New tool being built for accelerating Java development as part of Application Modernization service offering
Key Achievements and Challenges in the Last Month
Accomplished: All 4 Web Based Application Frameworks and 2 Desktop Application Frameworks are ready to be used Working on Cross Cutting Features Plan on HexNet and HexJava Factory integration sent for review Challenges: Consultants swapping and Project Extension underway
Project Execution
Training Needs | None | Agile Training Given
Critical Risks | None
Critical Issues | None
Open RR's
Review by Competency | Daily Standup Call by Product Owner, Weekly Review by Competency Head, Sprint Review every Two weeks
PHI | None given yet
Open NC / Observations of IQA | No Audits Done
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Sprint Four Completion |  |  |  |  | 2016-05-21 | 2016-05-21 | Complete
Sprint Three Completion |  |  |  |  | 2016-05-04 | 2016-05-04 | Complete
Separation of Framework Code and Reference Implementation Code |  |  |  |  | 2016-06-03 | 2016-06-03 | Complete
Cross Cutting Features Implementation |  |  |  |  | 2016-06-03 | 2016-06-03 | In Progress
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 0
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | No Open Issues |  | Number of post shipment defects
|  |  | Severity | 0 | 0 | 0 | 0
Software / Hardware Licensing
Software / Hardware Requested |  | None Open
Software / Hardware Availed |  | None Availed This Month

## ConsultantMatrix
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
RAVICHANDRAN MUTHU | PM | G8 | 10 | 2016-03-17 | 2016-06-03 | ADM
ISAAC JEFFERSON T | TM | G3 | 100 | 2016-03-21 | 2016-06-03 | ADM
KARTHIKEYAN RAJENDRAN | TM | G4 | 100 | 2016-03-21 | 2016-06-03 | ADM
JAYANTHI M | TM | G2 | 100 | 2016-03-21 | 2016-06-03 | ADM

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 20%
G3 | 6 | G3 | 1 | 20%
G5 | 1 | G4 | 2 | 40%
G6 | 2 | G5 |  | 0%
G7 | 1 | G6 |  | 0%
G8 | 2 | G7 |  | 0%
G4 | 3 | G8 | 1 | 20%
Grand Total | 16 | >G8 |  | 0%