## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - April 2016
Project Details
Project ID | PRJ-4713
Project Name | Equity Research Offering
Project Type | Development
Project Manager
Offerings / Unit | Equity Research Offering
Offering Owner | Pramit Joshi
Project Start Date | 2016-03-10
Project End Date | 2016-05-31
Tech Finance ID | 92526
Project Description
"Equity Research Offering is a solution to build and maintain ""Digital Equity Research"" on the Big Data Platform with the below features 1) Significantly reduces the time and energy of Equity Researcher in terms of collating news from various sources, aggregate structured (Financial Metrics) and Unstructured (Press Releases / Announcements) 2) Store in a central place and Process the information as required 3) Information Delivery mechanism to analyze the metrics and trends via Dashboards, and provide inputs to the equity research report"
Key Achievements and Challenges in the Last Month
Accomplished: Finalization of the First model which is to be implemented - 4/1/2016 - Completed NLG process for Highlights of the data interim Demo- 4/6/2016 - Completed As discussed with Pramit Interim Version demo - 4/18/2016 - Completed NLG process for Highlights of the data with Threshold enhancements - 4/18/2016 - Completed Mobile Version - 4/25/2016 - Completed Adding more security - 4/25/2016 - Completed Changes in dashboard from demo - 4/25/2016 - Completed Modelling Initial Version P/E multiple - 4/25/2016 - Completed Understanding of Financial Modeling, Valuation and Forecasting processes - Completed Challenges: Integration of Financial Model with ER framework
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
10-K Report Display |  |  |  |  | 2016-05-04 | 2016-05-04 | WIP
Populating Modelling input sheet for P/E multiple |  |  |  |  | 2016-05-04 | 2016-05-04 | WIP
Macro for P/E multiple |  |  |  |  | 2016-05-09 | 2016-05-09 | Yet to Start
Integrating P/E multiple with ER dashboard |  |  |  |  | 2016-05-09 | 2016-05-09 | Yet to Start
| New dashboard for Financial Modelling |  |  |  | 2016-05-18 | 2016-05-18 | Yet to Start
Final Version of the Analyst Report |  |  |  |  | 2016-05-18 | 2016-05-18 | WIP
Testing and corrections |  |  |  |  | 2016-05-31 | 2016-05-31 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 33.33%
G3 | 6 | G3 | 0 | 0%
G5 | 1 | G4 | 2 | 66.67%
G6 | 2 | G5 | 0 | 0%
G7 | 1 | G6 | 0 | 0%
G8 | 2 | G7 | 0 | 0%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%