## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Resume Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Context + is a text mining offering 1) Resume Analytics - To match the profile with the corresponding job description and rank them based on skill set, location, years of experience and other entity extracted from the profile. 2) Store in a central place and Process the information as required 3) Vector space model algorithm is used to rank the profiles.
Key Achievements and Challenges in the Last Month
Accomplished: Code Development - 30/4/2016 WIP Conversion of PDF documents into Text - 26/04/2016 Completed Updated Entity extraction - 25/04/2016 Completed Output in Tabular format. -25/04/2016 Completed Challenges: Ranking Prioritization based on the Business rules. Pre-Processing of the resumes.
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Entity extraction |  |  |  |  | TBD | TBD | WIP
| NLP and POS Tagging in the algorithm for Ranking Prioritization |  |  |  | TBD | TBD | WIP
Profile matching based on skill set |  |  |  |  | 2016-04-06 | 2016-04-01 | Completed
Prioritization based on the business rules |  |  |  |  | TBD | TBD | WIP
UI Development |  |  |  |  | TBD | TBD | WIP
Testing and corrections |  |  |  |  | TBD | TBD | Yet to start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G2
G2
G2

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 3 | 75%
G3 | 6 | G3 | 1 | 25%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16