## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID
Project Name | Governance Dashboard
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | Equity Research Offering
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-10
Project End Date | 2016-12-01
Tech Finance ID | 92514
Project Description
Governace Dashboard 1) It will allow the users to monitor the activity in the cluster such as jobs, data load etc.. 2) Data Growth monitoring 3) Data Usage monitoring
Key Achievements and Challenges in the Last Month
Accomplished: Metrics for the governance extracted - 3/11/2016 Completed Dashboard developed - 3/25/2016 Completed Challenges: Extraction of the metrics for governance
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Data Extraction |  |  |  |  | 2016-04-01 | 2016-04-01 | Completed
Dashboard development |  |  |  |  | 2016-03-25 | 2016-03-25 | Completed
Implemtation in Java Script |  |  |  |  | TBD | TBD | WIP
Testing and corrections |  |  |  |  | TBD | TBD | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
| Developer | G2 | 100
| Developer | G2 | 100

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 2 | 100%
G3 | 6
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16