## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Image Analytics is a offering 1) Detect factures in X-Ray images and to locate the facture area. 2) Object identification and to check the quality of the object in that image.
Key Achievements and Challenges in the Last Month
Accomplished: Platform setup - OpenCV Python - 4-April-2016(completed) Simple interface for bruteforce matcher - 5-April-2016(WIP) Challenges: Some functions are not able to build in opencv and working on it.
Project Execution
Training Needs | Training for Java/.Net | <mention the pending needs and challenges if any>
Critical Risks | No Risks Identified so far | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalization of the First model which is to be implemented |  |  |  |  | 2016-04-04 | 2016-01-04 | Completed
Adding new databases |  |  |  |  | TBD | TBD | WIP
Final Version of the Product |  |  |  |  | TBD | TBD | WIP
Testing and corrections |  |  |  |  | TBD | TBD | Yet to Start
OpenCV 3.0.0 environment setup with python; Requirement gathering for content based image recognition model and working on it. | [6 empty] | WIP
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Karthikeyan | Developer | G3 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG
Ragavendra | Developer | G3 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1
G3 | 6 | G3 | 2 | 100%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16