## -Context+
BIGLEAP Context +- Offering Monthly Status Report - May 2016
Project Details
Project ID | PRJ-4699
Project Name | Resume Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Context + is a text mining offering 1) Resume Analytics - To match the profile with the corresponding job description and rank them based on skill set, location, years of experience and other entity extracted from the profile. 2) Store in a central place and Process the information as required 3) Vector space model algorithm is used to rank the profiles.
Key Achievements and Challenges in the Last Month
Accomplished: Code Development - In progress Conversion of PDF documents into Text - Completed Entity extraction. - Completed Output in Tabular format. - Completed Challenges: Ranking Prioritization based on the Business rules. Pre-Processing of the resumes.
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Entity extraction and taxonomy building |  |  |  |  | 2016-02-05 | 16/5/16 | Completed
Profile matching based on business rules |  |  |  |  | 16/5/16 | 23/5/2016 | Completed
Prioritization based on the business rules |  |  |  |  | TBD | TBD | WIP
UI Development |  |  |  |  | TBD | TBD | Completed
Testing and corrections |  |  |  |  | TBD | TBD | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## MMA
MMA Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Image Analytics is a offering 1) Detect factures in X-Ray images and to locate the facture area. 2) Object identification and to check the quality of the object in that image.
Key Achievements and Challenges in the Last Month
Accomplished: Platform setup - OpenCV Python in Ubuntu - 31-May-2016(completed) Building all the needed function - 1-June-2016(completed) Challenges: Building imaging library requires time
Project Execution
Training Needs | Training for Python will be fine | <mention the pending needs and challenges if any>
Critical Risks | No Risks Identified so far | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Opencv installation on Windows |  |  |  |  | 20/5/2016 | 24/5/2016 | Not completed and the installation givers errors
Opencv installation in Ubuntu |  |  |  |  | 20/5/2016 | 24/5/2016 | Completed
Installing the binaries for opencv in ubuntu |  |  |  |  | 27/5/2016 | 30/5/2016 | Completed
Testing with the libraries |  |  |  |  | TBD | TBD | WIP
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## Governance Dashboard
Governance Dashboard Offering Monthly Status Report - March 2016
Project Details
Project ID
Project Name | Governance Dashboard
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | Equity Research Offering
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-10
Project End Date | 2016-12-01
Tech Finance ID | 92514
Project Description
Governace Dashboard 1) It will allow the users to monitor the activity in the cluster such as jobs, data load etc.. 2) Data Growth monitoring 3) Data Usage monitoring
Key Achievements and Challenges in the Last Month
Accomplished: Metrics for the governance extracted - 3/11/2016 Completed Dashboard developed - 3/25/2016 Completed Challenges: Extraction of the metrics for governance
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Data Extraction |  |  |  |  | 2016-04-01 | 2016-04-01 | Completed
Dashboard development using Chart.js |  |  |  |  | 2016-05-30 | 2016-06-10 | In progress
Implementation in Java Script |  |  |  |  | TBD | TBD | WIP
Creation of Login page |  |  |  |  | TBD | TBD | WIP
Exploring the metrics and architecture of Cloudera Navigator and Apache Falcon |  |  |  |  | TBD | TBD | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## Dr. Hadoop
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Dr.Hadoop is a Tool 1) It will analys the customers existing system and recommend hadoop system for the user 2) Auto deployement of the hadoop cluster
Key Achievements and Challenges in the Last Month
Accomplished: Weightage to questionair. ( completed) Store the answers in DB ( completed) Calculations based on the answers ( completed) UI development ( in progress)
Project Execution
Training Needs | Training for Java/.Net | <mention the pending needs and challenges if any>
Critical Risks | No Risks Identified so far | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Questionnaire Identification |  |  |  |  | 2016-04-04 | 2016-01-04 | Completed
| Prototype design | [5 empty] | Completed
Calculation for sizing |  |  |  |  | TBD | TBD | WIP
Scripts Generation |  |  |  |  | TBD | TBD | Yet to Start
UI Development |  |  |  |  | TBD | TBD | Yet to Start
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## Big Connect
Big Connect Offering Monthly Status Report - April 2016
Project Details
Project ID | PRJ-4699
Project Name | BIBA - Soultion - Bigleap
Project Type | Development
Project Manager | Ranga
Offerings / Unit | BIBA Service Offering
Offering Owner | Ranga
Project Start Date | 2016-02-01
Project End Date | 2016-12-31
Tech Finance ID
Project Description
Soltution for Metadata management and migration automation for various report and ETL tools. BIMA, DIMA, DART, INFAGEN, SQL PARSER, RLA , SLA, FIRE helps variours customer to capture metadata and doing automation of impact analysis & migraions.
Key Achievements and Challenges in the Last Month
Accomplished: login UI 02/05/2016 -WIP login ui 03/05/2016 - Completed login with user credentials -04/05/2016-WIP login with user credentials -05/05/2016-Completed home page UI -06/05/2016-Completed login UI for Destination-09/05/2016-WIP login UI for Destination-10/05/2016-Completed login for destination(Checking UNIX Access) 11/05/2016-WIP login for destination(Checking UNIX Access) 12/05/2016-Completed login for destination(Checking SQOOP Access) 13/05/2016-Completed login UI for Source-17/05/2016-WIP Login UI for source-18/05/2016-Completed Login for source for(Mysql and MSSQL)-19/05/2016-WIP Login for source for(Mysql and MSSQL)-20/05/2016-Completed Cheked Postgres Connection in localhost- 23/05/2016- Completed UI Design for Selecting Source Data -24/05/2016- Completed UI Design for Selecting Destination Data-25/05/2016- Completed checking source credentials -26/05/2016 -Completed checking dest credentials(unix and Sqoop)- 27/05/2016- Completed
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
identify DB2 instance |  |  |  |  | 2016-06-16 | 2016-06-16 | WIP
identify DB2 datatypes and hive mapping |  |  |  |  | 2016-06-10 | 2016-06-10 | WIP
generating sqoop scripts |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
testing generated sqoop scripts |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | Hardware: 64 Bit Cloud servers Softwares: Eclipse, JDK 1.7, MySQL 5.7, HDP 2.2

## ConsultantMatrix (hidden)
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G2
G2
G2

## Pivot (hidden)
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 3 | 75%
G3 | 6 | G3 | 1 | 25%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16