## MonthlyProjectStatus
DMO- March 2016
Project Details
Project ID
Project Name | Data Modernization Offering
Project Type | Development
Project Manager
Offerings / Unit | OEG
Offering Owner | Prasad Karkhanis
Project Start Date | 2016-03-10
Project End Date | 2017-12-31
Tech Finance ID
Project Description
Data Modernization solution provides automated way to migrate the data from point A to point B by making use of various solution components like HexaRule, DIMA Plus, Automaton, Data Recon etc. The tool helps organization to reduce the cost of delivery by automation and provides extreme flexibility to business users in handling the business rule at enforcing them into data validation process with minimal efforts
Key Achievements and Challenges in the Last Month
Accomplished: Data Profiler-Offline profiling and Remodeling of underlying data model -Completed Hexarule-Multi Project and Bug releases-Completed Automaton-Guiewire Data Setup-Completed Audit table for to support Migration health Dashbaord DASEM(Data Subsetting) Draft version -completed Challenges: Application Code integration with GIT
Project Execution
Training Needs | Workflow configuration in .net frame work | <mention the pending needs and challenges if any>
Open RR's
PHI | Actual:79.08
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Data Profiler -Batch Profiling- |  |  |  |  | 2016-03-31 | 2016-03-31 | Completed
Hexarule -Batch Profiling- |  |  |  |  | 2016-04-30 | 2016-04-30 | WIP
Automaton-Guidewire |  |  |  |  | 2016-03-31 | 2016-03-31 | Completed
Datarecon Release 1.4 |  |  |  |  | 2016-04-30 | 2016-04-30 | WIP
DASEM Release 1.4 |  |  |  |  | 2016-04-30 | 2016-04-30 | WIP
Java- Hexarule |  |  |  |  | 2016-04-15 | 2016-04-15 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 100%
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100%
Risks | All Risks are within control |  | Consultant Utilization % |  | 100%
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 7.143%
G3 | 6 | G3 | 4 | 28.57%
G5 | 1 | G4 | 2 | 14.29%
G6 | 2 | G5 | 4 | 28.57%
G7 | 1 | G6 | 2 | 14.29%
G8 | 2 | G7 | 1 | 7.143%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%