## MonthlyProjectStatus
DMO- March 2016
Project Details
Project ID
Project Name | Data Modernization Offering
Project Type | Development
Project Manager
Offerings / Unit | OEG
Offering Owner | Prasad Karkhanis
Project Start Date | 2016-03-10
Project End Date | 2017-12-31
Tech Finance ID
Project Description
Data Modernization solution provides automated way to migrate the data from point A to point B by making use of various solution components like HexaRule, DIMA Plus, Automaton, Data Recon etc. The tool helps organization to reduce the cost of delivery by automation and provides extreme flexibility to business users in handling the business rule at enforcing them into data validation process with minimal efforts
Key Achievements and Challenges in the Last Month
Accomplished: Profiler: Offline profiling on multiple tables Re modelling to enhance the reporting and dashboard capabilities Expression Builder feature to apply SQL function on comparison columns Enabled batch process statistics for the loaded data to do the Audit Analytics Automaton: Auto Search with in the Mapping grid to link Target to Source objects Including business Rule while configuring the Transformation logic Rearranging the view display for the Mapping template Built Guide wire data model for claim center migration Enabled batch process statistics for the loaded data to do the Audit Analytics Hexarule: Built Guide wire data model for claim center migrations Created hygiene rule configuration created based on profiled data Enabled Error process statistics for the cleansed data to do the Audit Analytics DATARECON: Expression Builder feature to apply SQL function on comparison columns Enabled batch process statistics for the loaded data Challenges: Application Code integration with GIT Java API building for Pentaho
Project Execution
Training Needs | Workflow configuration in .net frame work | <mention the pending needs and challenges if any>
Open RR's
PHI | Actual:79.08
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Data Profiler Release--1.3&-2.1- |  |  |  |  | 2016-04-29 | 2016-04-29 | Completed
Hexarule -Release -1.3&-2.1 |  |  |  |  | 2016-04-29 | 2016-04-29 | WIP
Automaton-Release -1.3&-2.1 |  |  |  |  | 2016-04-29 | 2016-04-29 | Completed
Datarecon Release -1.3&-2.1 |  |  |  |  | 2016-04-29 | 2016-04-29 | WIP
DASEM Release -1.3&-2.1 |  |  |  |  | 2016-04-29 | 2016-04-29 | WIP
Infagen--1.3&-2.1 |  |  |  |  | 2016-04-29 | 2016-04-29 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 100%
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100%
Risks | All Risks are within control |  | Consultant Utilization % |  | 100%
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 7.143%
G3 | 6 | G3 | 4 | 28.57%
G5 | 1 | G4 | 2 | 14.29%
G6 | 2 | G5 | 4 | 28.57%
G7 | 1 | G6 | 2 | 14.29%
G8 | 2 | G7 | 1 | 7.143%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%