## MonthlyProjectStatus
DMO- March 2016
Project Details
Project ID
Project Name | Data Modernization Offering
Project Type | Development
Project Manager
Offerings / Unit | OEG
Offering Owner | Prasad Karkhanis
Project Start Date | 2016-03-10
Project End Date | 2017-12-31
Tech Finance ID
Project Description
Data Modernization solution provides automated way to migrate the data from point A to point B by making use of various solution components like HexaRule, DIMA Plus, Automaton, Data Recon etc. The tool helps organization to reduce the cost of delivery by automation and provides extreme flexibility to business users in handling the business rule at enforcing them into data validation process with minimal efforts
Key Achievements and Challenges in the Last Month
.net Accomplished: Training Manual and Instruction Manual for each Module similar to Infagena nd Automaton Profiler: Including record count in Code Management Option Automaton: load excel to be renamed as Data Management in Automaton with option of upload and Download Define Parament Value Data upload utility to support multiple file types Data Type Template Hexarule: Execution of HaxaRule process in Offline Mode DATARECON: Master Setup: Audit Process -Orchestration UI Audit Process -Workflow Process Orchestration -UI Chang Java Bug Fixes in Hexarule Home Page and Integration Hexarule documentation POCs in Progress Xerox ICMA UCMS Challenges: Application Code integration with GIT Java API building for Pentaho SSIS .Net skilled person to replace suganya
Project Execution
Training Needs | Workflow configuration in .net frame work | <mention the pending needs and challenges if any>
Open RR's
PHI | Actual:87
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Hexarule -Release 2.2 |  |  |  |  | 2016-05-31 | 2016-05-31 | Completed
Automaton-Release -2.2 |  |  |  |  | 2016-05-31 | 2016-05-31 | Completed
DASEM Release -2.2 |  |  |  |  | 2016-05-31 | 2016-05-31 | Completed
Java Hexarule |  |  |  |  | 2016-05-31 | 2016-05-31 | Completed
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 100%
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100%
Risks | All Risks are within control |  | Consultant Utilization % |  | 100%
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 2 | 13.33%
G3 | 6 | G3 | 4 | 26.67%
G5 | 1 | G4 | 1 | 6.667%
G6 | 2 | G5 | 4 | 26.67%
G7 | 1 | G6 | 2 | 13.33%
G8 | 2 | G7 | 2 | 13.33%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%