## MonthlyProjectStatus
IoT Offering Monthly Status Report - May 2016
Project Details
Project ID
Project Name | IoT & Analytics Offering
Project Type | Development
Project Manager
Offerings / Unit | IoT & Analytics Offering
Offering Owner | Innovation Lab
Project Start Date | 2016-03-10
Project End Date | 2016-12-31
Tech Finance ID
Project Description
IoT Offering is a solution to monitor and manage assets on the Key telematics Platform with the below features : 1) Monitor Key events and produce alerts. 2) Store sensor data in a central place and process the information as required. 3) Predictive Analytics via Dashboards for making informed decisions.
Key Achievements and Challenges in the Last Month
Accomplished: Tableau dashboard is updated using data generated from Hexaware vehicles - 5/13/2016 Completed Evaluation - storage / extraction of Telemetry data from streaming API is tested with MongoDB 5/28/2016 Completed Risk exposure analysis - Additional case for Usage based Insurance concepts for vehicles(Visualization using Tableau) 5/28/2016 Completed Challenges: Due to insufficient data performing time series analysis for fact based pricing is now challenging and so the task has been dropped.
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
IoT garage Phase 1 implementations |  |  |  |  | 2016-08-31 | 2016-08-31 | Yet to Start
Evaluation - storage / extraction of Telemetry data from streaming API is tested with MongoDB |  |  |  |  | 2016-05-31 | 2016-05-28 | Completed
Risk exposure analysis (Visualization using Tableau) |  |  |  |  | 2016-05-31 | 2016-05-28 | Completed
Developing predictive models to estimate fuel consumption per vehicle |  |  |  |  | 2016-06-10 | 2016-06-10 | In Progress
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Grade | No. of consultant | % of Total FTE
G2 | 3 | 75%
G3 | 0 | 0%
G4 | 0 | 0%
G5 | 1 | 25%
G6 | 0 | 0%
G7 | 0 | 0%
G8 | 0 | 0%
>G8 |  | 0%