## MonthlyProjectStatus
IoT Offering Monthly Status Report - March 2016
Project Details
Project ID
Project Name | IoT & Analytics Offering
Project Type | Development
Project Manager
Offerings / Unit | IoT & Analytics Offering
Offering Owner | Innovation Lab
Project Start Date | 2016-03-10
Project End Date | 2016-12-31
Tech Finance ID
Project Description
IoT Offering is a solution to monitor and manage assets on the Key telematics Platform with the below features : 1) Monitor Key events and produce alerts. 2) Store sensor data in a central place and process the information as required. 3) Predictive Analytics via Dashboards for making informed decisions.
Key Achievements and Challenges in the Last Month
Accomplished: Finalization of IoT garage use cases & initial team formation- 3/16/2016 Completed Devices analysis and finalization with vendors - 3/23/2016 Completed Initial data extraction for vehicle telematics -3/31/2016 Completed Interactive cluster graphs using plotly is implemented - 4/15/2016 Completed Tableau dashboard is updated using data generated from new vehicles - 4/18/2016 Completed Challenges: Additional resources are needed to step up tasks. Data can be generated once the devices are procured from Vendors. Tableau dashboard in the cloud performs slow when multiple users are accessing to it parallely
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | 1 | Online tableau server is down. Ticket has been raised with Tableau.
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalization of the IoT Garage Use cases - Phase 1 |  |  |  |  | 2016-03-20 | 2016-03-20 | Completed
Gosafe devices data extraction |  |  |  |  | 2016-03-31 | 2016-03-31 | Completed
Interactive cluster graphs using plotly is implemented |  |  |  |  | 2016-04-15 | 2016-04-15 | Completed
Tableau dashboard for new vehicles with Gosafe devices |  |  |  |  | 2016-04-18 | 2016-04-18 | Completed
IoT garage Phase 1 implementations |  |  |  |  | 2016-07-31 | 2016-07-31 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Grade | No. of consultant | % of Total FTE
G2 | 2 | 66.67%
G3 | 0 | 0%
G4 | 0 | 0%
G5 | 1 | 33.33%
G6 | 0 | 0%
G7 | 0 | 0%
G8 | 0 | 0%
>G8 |  | 0%