## MonthlyProjectStatus
BIBA Metadata Accelerators Offering Monthly Status Report - April 2016
Project Details
Project ID | PRJ-4656
Project Name | BIBA - Soultion - BI Metadata_Accelerators
Project Type | Maintenance
Project Manager | Murugesh Pandian Meenapandi
Offerings / Unit | BIBA Service Offering
Offering Owner | Murugesh Pandian Meenapandi
Project Start Date | 2016-02-01
Project End Date | 2016-12-31
Tech Finance ID | 92517
Project Description
Soltution for Metadata management and migration automation for various report and ETL tools. BIMA, DIMA, DART, INFAGEN, SQL PARSER, RLA , SLA, FIRE helps variours customer to capture metadata and doing automation of impact analysis & migraions.
Key Achievements and Challenges in the Last Month
Accomplished: BIMA for BO(Webi and Restful) -Added code to update Refresh on open property of Webi Documents for capture Query without facing any error - 5/2/2016 Completed BIMA BO 4.1 deployment for Hermes- 5/3/2016Completed BIMA for BO ,BIMA for Crystal,SQL Parser,DART,BIMA for SSRS Demo to First Solar -5/5/2016 Completed BIMA for WebI 4.1 Executable jar creation - 5/4/2016Completed Extraction of Catalent Report BO 4.1 (Phase2)- 5/3/2016 Completed BIMA-MSTR,SLA,RLA for MSTR Demo to DB - 5/6/2016Completed Duplicate Analysis report for Catalent(Created mapping in informatica)- 5/6/2016 Completed Deployed the following tools SQL Parser,DART,BIMA for SSRS in first solar - 5/6/2016 Completed Created log file for SLA tool - 5/4/2016Completed Internal Demo BIMA SSRS, DART-5/10/2016 Completed Developed BIMA SSRS Metadata Analysis, Complexity Analysis,Duplicate Analysis Reports and Published into server - 5/11/2016 Completed Developed Home Page in SLA for Bo 4.1 Tool - 5/12/2016 Completed Developed Configuration Page in SLA for Bo 4.1 Tool -5/13/2016 Completed Fron End Changes and added Metadata viewer link in BIMA for MSTR - 5/18/2016 Completed Duplicate Report creation and Metadata Analysis Report Changes in MSTR - 5/19/2016 Completed BIMA for MSTR,BO to MSTR Demo to DB Client - 5/19/2016 Completed SLA for BO 4.1-created business Layer with one dimension -5/24/2016Completed RLA SSRS -Multiple Tab to Multiple Report and Captured datatype information in BIMA -5/27/2016 Completed Integrated BIMA for Cognos and SLA for BO Latest code- 5/27/2016 Completed
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
RLA for SSRS Enhancements |  |  |  |  | 2016-06-16 | 2016-06-16 | WIP
Enhancements in RLA for BO 4.1-Test the tool with latest version of BO |  |  |  |  | 2016-06-10 | 2016-06-10 | WIP
WebInterface of BIMA,SLA,RLA for BO Creation |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
Cognos Framework to BO Universe (SLA Tool Creation) |  |  |  |  | 2016-06-30 | 2016-06-30 | WIP
BO to SSRS deployment in BNP |  |  |  |  | 2016-06-10 | 2016-06-10 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | Hardware: 64 Bit Cloud servers Softwares: .Net 3.5 or above, Java JDK & JRE 1.7 or above, Eclipse, Visual Studio 2008 & 2013, SQL server 2008 & 2012, Apache Tomcat 6 or above, JBOSS Open Source Frameworks & Softwares: .Net Framework 3.5 or above, Java JDK & JRE 1.7 or above.

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Parkavi P | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Usha Gomathi M | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Deepak Kumar K | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Revathi K | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Rahimuddin Mohammed | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Imran | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G3 | 6 | G2 | 0 | 0%
Grand Total | 6 | G3 | 5 | 100%
|  | G4 | 0 | 0%
|  | G5 | 0 | 0%
|  | G6 | 0 | 0%
|  | G7 | 0 | 0%
|  | G8 | 0 | 0%
|  | >G8 |  | 0%