## MonthlyProjectStatus
PRJ-3997-OEG_ADM_Agile_DevOps_Lab_Monthly Status Report - March 2016
Project Details
Project ID | PRJ-3997
Project Name | OEG_ADM_Agile DevOps Lab
Project Type | Development
Project Manager | RAVICHANDRAN MUTHU
Offerings / Unit | Agile DevOps Service Offering / ADM
Offering Owner | Prasad Surkund
Project Start Date | 2015-03-10
Project End Date | 2016-06-30
Tech Finance ID | 95806
Project Description
Setup an Agile DevOps Lab for client showcasing & walkthroughs; Agile CoE work; Execute Internal PoC's and Projects using Hexa Agile Frameworks, Models & Methodologies.
Key Achievements and Challenges in the Last Month
Accomplished: Project renewed for another three months and process set for renewal after review every three months. AWS Workshop and AppDynamics Webinar given for team to plan for integration into our framework Kanban Training given for Team. Best practices to be implemented after finalization by Agile Coach VSTS DevOps - Automated flow set for automated testing Apache jMeter Performance testing tool integration - Java done - Under Review Challenges: None Major
Training Needs | None
Critical Risks | None
Critical Issues | None
Open RR's | None
Review by Competency | Weekly Review by Service Offering Owner
PHI | Not done yet
Open NC / Observations of IQA | No Audits done
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Project Renewal |  |  |  |  | 2016-03-31 | 2016-03-31 | Complete
jMeter Integration for Java and Dotnet |  |  |  |  | 2016-04-15 |  | In Progress
VSTS Full Flow for Dotnet |  |  |  |  | 2016-04-15 |  | In Progress
Transition to IMS |  |  |  |  | 2016-04-30 |  | On Hold
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 0
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | None |  | Number of post shipment defects
|  |  | Severity | 0 | 0 | 0 | 0
Software / Hardware Licensing
Software / Hardware Requested |  | None open
Software / Hardware Availed |  | None availed this month

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Ravichandran Muthu | PM | G8 | 50% | 2015-03-23 | 2016-06-30 | ADM
Vivek Gole | TM | G5 | 100% | 2015-03-27 | 2016-06-30 | ADM
Reena Elizabeth P | TM | G5 | 100% | 2015-04-17 | 2016-06-30 | ADM
Indumathi Sundaramurthy | TM | G3 | 100% | 2015-04-01 | 2016-06-30 | DA

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 0 | 0%
G3 | 6 | G3 | 1 | 25%
G5 | 1 | G4 | 0 | 0%
G6 | 2 | G5 | 2 | 50%
G7 | 1 | G6 | 0 | 0%
G8 | 2 | G7 | 0 | 0%
G4 | 3 | G8 | 1 | 25%
Grand Total | 16 | >G8 |  | 0%