## MonthlyProjectStatus
Akiva Status Report - March 2016
Project Details
Project ID | PRJ-4352 - HR-IT Take-Akiva - 92516
Project Name | Akiva upgrade from java1.5 to 1.8 for PGE, VIACOM and Columbia
Project Type | Development
Project Manager | Krishna Patel
Offerings / Unit | OEG
Offering Owner | Venkatesan Ladapuram K
Project Start Date | 2016-03-14
Project End Date | 2016-05-15
Tech Finance ID | 92516
Project Description
PGE: Requirement is to make Akiva compatible with 12c container pluggable DB. This requires to upgradeakiva compatible with Java version 1.5 to 1.8 . Post the upgrade implement akiva in PGE . VIACOM: Upgrade akiva HRMS compatible with 12c and implement in viacom. Columbia: Enhance Akiva to support kerberos single sign on.
Key Achievements and Challenges in the Last Month
Accomplished: Upgraded TOMCAT 5.5 to 6 and made it compatible with Java 1.5 to Java 1.8 Verified and upgraded all the libraries and classes which need to be packaged Certified all the PL/SQL on oracle 12c container pluggable DB Trouble shooted and conducted RCA for all the errors which came across during the course of upgrade Upgraded spring 2.5 to Spring 4 ,Configuration and setup completed Packaging is in progress Challenges: Packaging challengesas as Akiva is not working in some systems, in some systems it's working fine. Started analyzing the code Columbia code for kerberos.
Project Execution
Training Needs | Team requires packaging training | <mention the pending needs and challenges if any>
Critical Risks | Several Different versions at client site | <Refer critical risks from PP>
Critical Issues | 2 | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Upgrade tomcat , spring and fix all the errors |  |  |  |  | 2016-08-04 | 2016-01-04 | Completed
Complete code changes |  |  |  |  | 15/4/2016 | 2016-08-04 | WIP
Complete packaging |  |  |  |  | 20/4/2016 | 15/4/2016 | WIP
Certify akiva on 12c |  |  |  |  | 31/04/2016 | 15/04/2016 | WIP
implement at PGE |  |  |  |  | 2016-04-20 | 2016-04-26 | Yet to Start
Implement at VIACOM |  |  |  |  | 15/4/2016 | 15/4/2016 | WIP
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Abdul aleem shaik |  | G3 | 100
Hareesh severaj |  | G3 | 100
Thomas vargheese |  | G4 | 100
veera vijay |  | G4 | 50
Krishna kishore patel |  | G7 | 25

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G3 | 2 | G2 | 0 | 0%
G7 | 1 | G3 | 3 | 50%
G4 | 2 | G4 | 2 | 33.33%
Grand Total | 5 | G5 | 0 | 0%
|  | G6 | 0 | 0%
|  | G7 | 1 | 16.67%
|  | G8 | 0 | 0%
|  | >G8 |  | 0%