## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID
Project Name | Equity Research Offering
Project Type | Development
Project Manager
Offerings / Unit | Equity Research Offering
Offering Owner | Pramit Joshi
Project Start Date | 2016-03-10
Project End Date | 2016-05-31
Tech Finance ID
Project Description
"Equity Research Offering is a solution to build and maintain ""Digital Equity Research"" on the Big Data Platform with the below features 1) Significantly reduces the time and energy of Equity Researcher in terms of collating news from various sources, aggregate structured (Financial Metrics) and Unstructured (Press Releases / Announcements) 2) Store in a central place and Process the information as required 3) Information Delivery mechanism to analyze the metrics and trends via Dashboards, and provide inputs to the equity research report"
Key Achievements and Challenges in the Last Month
Accomplished: Financial ratios Dashboard - 3/16/2016 Completed Section content from 10-K - 3/23/2016 Completed Clarification of the Equity Research Output - 3/23/2016 Completed Finalization of the Output Format with Pramit -3/23/2016 Completed Challenges: Understanding of Financial Modeling, Valuation and Forecasting processes Once after understanding the above - Finalization of what needs to be accomplished as part of our offering
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalization of the First model which is to be implemented |  |  |  |  | 2016-04-01 | 2016-04-01 | Completed
NLG process for Highlights of the data Sample version |  |  |  |  | 2016-04-06 | 2016-04-06 | WIP
As discussed with Pramit Interim Version demo |  |  |  |  | 2016-04-18 | 2016-04-18 | WIP
Final Version of the Analyst Report |  |  |  |  | 2016-05-18 | 2016-05-18 | WIP
Testing and corrections |  |  |  |  | 2016-05-31 | 2016-05-31 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 2 | 50%
G3 | 6 | G3 | 0 | 0%
G5 | 1 | G4 | 2 | 50%
G6 | 2 | G5 | 0 | 0%
G7 | 1 | G6 | 0 | 0%
G8 | 2 | G7 | 0 | 0%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%