## MonthlyProjectStatus
IoT Offering Monthly Status Report - March 2016
Project Details
Project ID
Project Name | IoT & Analytics Offering
Project Type | Development
Project Manager
Offerings / Unit | IoT & Analytics Offering
Offering Owner | Innovation Lab
Project Start Date | 2016-03-10
Project End Date | 2016-12-31
Tech Finance ID
Project Description
IoT Offering is a solution to monitor and manage assets on the Key telematics Platform with the below features : 1) Monitor Key events and produce alerts. 2) Store sensor data in a central place and process the information as required. 3) Predictive Analytics via Dashboards for making informed decisions.
Key Achievements and Challenges in the Last Month
Accomplished: Finalization of IoT garage use cases & initial team formation- 3/16/2016 Completed Devices analysis and finalization with vendors - 3/23/2016 Completed Initial data extraction for vehicle telematics -3/31/2016 Completed Challenges: Additional resources are needed to step up tasks. Data can be generated once the devices are procured from Vendors.
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | 1 | Online tableau server is down. Ticket has been raised with Tableau.
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalization of the IoT Garage Use cases - Phase 1 |  |  |  |  | 2016-03-20 | 2016-03-20 | Completed
Gosafe devices data extraction |  |  |  |  | 2016-03-31 | 2016-03-31 | Completed
Tableau dashboard for new vehicles with Gosafe devices |  |  |  |  | 2016-04-18 | 2016-04-18 | WIP
IoT garage Phase 1 implementations |  |  |  |  | 2016-07-31 | 2016-07-31 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Grade | No. of consultant | % of Total FTE
G2 | 2 | 66.67%
G3 | 0 | 0%
G4 | 0 | 0%
G5 | 1 | 33.33%
G6 | 0 | 0%
G7 | 0 | 0%
G8 | 0 | 0%
>G8 |  | 0%