## MonthlyProjectStatus
OEG_ES_CloudMorphy Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4353
Project Name | OEG_ES_CloudMorphy
Project Type | Maintenance
Project Manager | Pazhani Velu Deivasigamani
Offerings / Unit | Innovation Lab
Offering Owner | OEG_ES
Project Start Date | 2016-05-01
Project End Date
Tech Finance ID
Project Description
‘CloudMorphy’ is Hexaware’s IP Accelerator for migrating enterprise applications to Cloud-based / On-premise enterprise applications. It has been successfully used in several Fusion implementation projects and tested across Fusion, Workday, PeopleSoft and SAP. The current sales model of ‘CloudMorphy’ has hit a roadblock with customers demanding a shift to an as-a-service model. Customers no longer want to buy software – instead, they are demanding a hosted or cloud service. This project is a feasibility study about moving the .NET based ‘CloudMorphy’ tool from an On-premise / license model to a SaaS model.
Key Achievements and Challenges in the Last Month
Accomplished: Walk-through by Program Manager for Project Manager; Team formed with PM and one .NET Architect; KT completed between leaver and incomer; Selection of an external candidate as back-fill; Latest Source Code moved to GIT HUB; Acquired Cloudserver for CloudMorphy SQLServer DB; Acquired Instances for CloudMorphy demo with PeopleSoft, SAP, Workday and Fusion; MS Azure training to CloudMorphy team; SaaS feasibility study document ready Challenges: Availability of knowledgeable Functional resources for end-to-end demo for Fusion, SAP and Workday
Project Execution
Training Needs | <any training pending> | Team has undergone MS Azure Training
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's | 59443 | Joining on 21st May
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Share SaaSification feasibility study report with Venkataraman A R | [5 empty] | 6th April 2016 | Validation
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | CloudServer 4 Core, 8 GB RAM, C Drive 50 GB and D Drive 50 GB with Windows Server 2012 STD, IIS, MSSQLServer
Software / Hardware Availed |  | CloudServer 4 Core, 8 GB RAM, C Drive 50 GB and D Drive 50 GB with Windows Server 2012 STD, IIS, MSSQLServer

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
Deivasigamani Pazhanivelu | PM | G8 | 100 |  |  | MS
Vignesh muthiah Chidambaram | .NET Architect | G4 | 100 |  |  | DCCRM
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 |  | 0%
G3 | 6 | G3 |  | 0%
G5 | 1 | G4 | 1 | 50%
G6 | 2 | G5 |  | 0%
G7 | 1 | G6 |  | 0%
G8 | 2 | G7 |  | 0%
G4 | 3 | G8 | 1 | 50%
Grand Total | 16 | >G8 |  | 0%