## MonthlyProjectStatus
Jumbo - Hadoop Testing Tool - Monthly Status Report - Mar-16
Project Details
Project ID | PRJ-4356
Project Name | OEG_DA_Hadoop Testing tool Jumbo
Project Type | Development
Project Manager | Arunachalam
Offerings / Unit | Data Centric Services
Offering Owner | Arunachalam
Project Start Date | 2016-01-01
Project End Date | 2016-06-30
Tech Finance ID | 92518
Project Description
To create a platform which would support data validation of RDBMS and non RDBMS data in Hadoop The major goals of the tool : 1. To verify if the source table/column values are available in target table/columns (The Source/target mapping to be given as an input) 2. To display specific data quality metrics regarding the db - no. of null columns, their values (%) - specific format violations % (for eg. email, date , telephone formats etc.)
Key Achievements and Challenges in the Last Month
Accomplished: Base version development completed Testing Completed Bug Fixing in progress Challenges: Performance Improvement
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Bug Fixes |  |  |  |  | 2016-04-15 |  | In Progress
Version 2 Requirement Documentation |  |  |  |  | 2016-04-29 |  | In Progress
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 |  | 0%
G3 | 6 | G3 | 1 | 50%
G5 | 1 | G4 | 1 | 50%
G6 | 2 | G5 |  | 0%
G7 | 1 | G6 |  | 0%
G8 | 2 | G7 |  | 0%
G4 | 3 | G8 |  | 0%
Grand Total | 16 | >G8 |  | 0%