## MonthlyProjectStatus
PRJ-4693-OEG_ADM_AM_HEXJAVA_SWFACTORY_Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4693
Project Name | OEG_ADM_Application_Portfolio_Analysis_Suite
Project Type | Development
Project Manager | RAVICHANDRAN MUTHU
Offerings / Unit | Application Modernization and Integrated ASM / ADM
Offering Owner | Santhosh Kumar Ramabadhran and Sushil Karambelkar
Project Start Date | 2016-01-06
Project End Date | 2016-03-31
Tech Finance ID | 95806
Project Description
Tool to capture and analyse Application Portfolio
Key Achievements and Challenges in the Last Month
Accomplished: Followed up on Project Scope to change state from on hold Challenges: Project approach was not finalized on customizing a market product or going ahead with custom development of the tool
Project Execution
Training Needs | None | Agile Training Given
Critical Risks | None
Critical Issues | None
Open RR's
Review by Competency | Daily Standup Call by Product Owner, Weekly Review by Competency Head, Sprint Review every Two weeks
PHI | None given yet
Open NC / Observations of IQA | No Audits Done
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Project Closure |  |  |  |  | 2016-03-31 | 2016-03-31 | Closed
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance |  | 0
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | No Open issues |  | Number of post shipment defects
|  |  | Severity | 0 | 0 | 0 | 0
Software / Hardware Licensing
Software / Hardware Requested |  | None
Software / Hardware Availed |  | None

## ConsultantMatrix
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
RAMACHANDIRAN D | TM | G4 | 100 | 2016-01-11 | 2016-03-31 | ADM

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 25%
G3 | 6 | G3 | 1 | 25%
G5 | 1 | G4 | 1 | 25%
G6 | 2 | G5 |  | 0%
G7 | 1 | G6 |  | 0%
G8 | 2 | G7 |  | 0%
G4 | 3 | G8 | 1 | 25%
Grand Total | 16 | >G8 |  | 0%