## MonthlyProjectStatus
PRJ-4363 Monthly Status Report - Mar 2016
Project Details
Project ID | PRJ-4363
Project Name | Self-Heal PoC
Project Type | Development
Project Manager | Ramkumar NJ
Offerings / Unit | ES
Offering Owner | Madhavi
Project Start Date | 2015-09-21
Project End Date | 2016-12-31
Tech Finance ID | 95810
Project Description
PoC for creation of a framework that can automatically detect and resolve issue in Enterprise Applications
Key Achievements and Challenges in the Last Month
Accomplished: * Creation of a repeatable framework for deduction and resolution of issue with 1-to-1 relationship between issue and resolution - Aware * Aware PoC tested for all 3 major ERPs - PeopleSoft, SAP & Oracle e-Biz * Aware can work on SQL based deduction/resolution and Service call based deduction/resolution * Currently extending the application for more use cases in eBiz Challenges:
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | 1 | Dependency to Summit
Critical Issues | 1 | Support from Summit is not as it used to be before
Open RR's
Review by Competency | 2016-04-05 | * Extension of Aware for eBiz usecases * Identification of Projects to Pilot
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Ramkumar NJ | Architect & PM | G8 | 50 | 2015-09-21 | 2016-12-31 | PeopleSoft-Dev
Vinoth Rajarathinam | Team Member | G4 | 100 | 2016-02-15 | 2016-12-31 | Competency Dev - MS
Praveen Raj | Team Member | G3 | 100 | 2016-03-01 | 2016-12-31 | Competency Dev - Oracle

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G3 | 1 | G2 | 0 | 0%
G8 | 1 | G3 | 1 | 33.33%
G4 | 1 | G4 | 1 | 33.33%
Grand Total | 3 | G5 | 0 | 0%
|  | G6 | 0 | 0%
|  | G7 | 0 | 0%
|  | G8 | 1 | 33.33%
|  | >G8 |  | 0%