## MonthlyProjectStatus
Akiva Status Report - March 2016
Project Details
Project ID | PRJ-4352 - HR-IT Take-Akiva - 92516
Project Name | [PRJ-4352]OEG_ES_PS_Akiva
Project Type | Maintenance
Project Manager | Krishna Patel
Offerings / Unit | OEG
Offering Owner | Venkataraman A r
Project Start Date | 2015-09-21
Project End Date | 2016-12-31
Tech Finance ID | 92516
Project Description
PGE: Requirement is to make Akiva compatible with 12c container pluggable DB. This requires to upgrade akiva compatible with Java version 1.5 to 1.8 . Post the upgrade implement akiva in PGE for FSCM and then for HCM. VIACOM: Upgrade akiva HRMS compatible with 12c and implement in viacom. Address all the issues arise in VIACOM implementation. Columbia: Enhance Akiva to support kerberos single sign on.
Key Achievements and Challenges in the Last Month
Accomplished: PGE : Upgraded TOMCAT 5.5 to 6 and made it compatible with Java 1.5 to Java 1.8, Verified and upgraded all the libraries and classes which need to be packaged, Certified all the PL/SQL on oracle 12c container pluggable DB, Trouble shooted and conducted RCA for all the errors which came across during the course of upgrade, Upgraded spring 2.5 to Spring 4 ,Configuration and setup completed, Packaging is completed for FSCM , Packaging completed for HRMS, prepared installation , configuration documents and uploaded the code in to GIT. Waiting for PGE team to install akiva and let us know if there is any issues. COLUMBIA EDU: Addressed the issues COLUMBIA is facing with respect to masking the fields, have provided Demo as per their request. Installed Kerberos in systems Challenges: Not able to replicate the kerberos Issues which COLUMBIA client is facing VIACOM : Packaging completed for HRMS, prepared installation , configuration documents and uploaded the code in to GIT.
Project Execution
Training Needs | Team requires kerberos training from Columbia | <mention the pending needs and challenges if any>
Critical Risks | Several Different versions at client site | <Refer critical risks from PP>
Critical Issues | 1 | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Complete akiva packaging FSCM Akiva |  |  |  |  | 30/04/2016 | 30/04/2016 | Completed
Complete akiva packaging HCM Akiva |  |  |  |  | 30/04/2016 | 20/04/2016 | Completed
Implement at PGE |  |  |  |  | 2016-05-15 | 2016-05-01 | Yet to Start
Implement at VIACOM |  |  |  |  | 15/4/2016 | 2016-12-04 | Completed
Implement Kerberos enabled Akiva for Columbia |  |  |  |  | TBD | TBD | WIP
Fixing issues at viavom |  |  |  |  | 30/4/2016 | 30/4/2016 | Completed
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track(15 DAYS AHEAD of scheduled due date) |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | 3 |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | VM WARE WINDOWS 12 SERVERS 172.25.164.168, 172.25.100.72, 172.25.164.205,10.1.55.196

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Abdul aleem shaik |  | G3 | 100
Hareesh severaj |  | G3 | 100
Thomas vargheese |  | G4 | 100
veera vijay |  | G4 | 50
Krishna kishore patel |  | G7 | 75

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G3 | 2 | G2 | 0 | 0%
G7 | 1 | G3 | 3 | 50%
G4 | 2 | G4 | 2 | 33.33%
Grand Total | 5 | G5 | 0 | 0%
|  | G6 | 0 | 0%
|  | G7 | 1 | 16.67%
|  | G8 | 0 | 0%
|  | >G8 |  | 0%