## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Image Analytics
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
Dr.Hadoop is a Tool 1) It will analys the customers existing system and recommend hadoop system for the user 2) Auto deployement of the hadoop cluster
Key Achievements and Challenges in the Last Month
Accomplished: calculation prototype is finished - 4-April-2016(completed) calculation based on the questionire using jsp is work in progress - 16-April-2016(completed) Challenges: Generation of the scripts.
Project Execution
Training Needs | Training for Java/.Net | <mention the pending needs and challenges if any>
Critical Risks | No Risks Identified so far | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Questionnaire Identification |  |  |  |  | 2016-04-04 | 2016-01-04 | Completed
| Prototype design | [5 empty] | Completed
Calculation for sizing |  |  |  |  | TBD | TBD | WIP
Scripts Generation |  |  |  |  | TBD | TBD | Yet to Start
UI Development |  |  |  |  | TBD | TBD | Yet to Start
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Kingsly | Developer | G3 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG
Sweeklin | Developer | G2 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 50%
G3 | 6 | G3 | 1 | 50%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16