## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | Optical Character Recognization
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-01-05
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
OCR is a part of image offering 1) Convert text images into a text file 2) Store the text in a central place. 3) Compare the input image with the converted text file
Key Achievements and Challenges in the Last Month
Accomplished: Study of technology to be implemented. - 25/04/2016 Completed Traning the data based on the requirement using neural network. - 30/04/2016 WIP Challenges: Training the system with different fonts. Pre-processing the input image to achieve accuracy.
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Training data in different fonts |  |  |  |  | 2016-04-01 | 2016-04-01 | WIP
| Researching about deep learning and algorithm supporting OCR | [5 empty] | Completed
| Implementing the algorithm | [5 empty] | WIP
Image with good quality and font |  |  |  |  | 2016-04-06 | 2016-04-06 | Completed
Implementation in hadoop |  |  |  |  | 2016-04-18 | 2016-04-18 | Yet to Start
UI Development and intergration |  |  |  |  | 2016-05-18 | 2016-05-18 | Yet to Start
Testing and corrections |  |  |  |  | 2016-05-31 | 2016-05-31 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Hariharavignesh |  | G3 | 100 | 2016-03-01 | 2016-12-01 | OEG
Naveena |  | G2 | 100 | 2016-03-01 | 2016-12-01 | OEG

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 50%
G3 | 6 | G3 | 1 | 50%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16