## MonthlyProjectStatus
Equity Research Offering Monthly Status Report - March 2016
Project Details
Project ID | PRJ-4699
Project Name | HexaConnect
Project Type | Development
Project Manager | Ranganathan Rajkumar
Offerings / Unit | OEG
Offering Owner | Ranganathan Rajkumar
Project Start Date | 2016-03-01
Project End Date | 2016-12-31
Tech Finance ID | 92514
Project Description
HexaConnect is a tool to ingest data into hadoop 1) Significantly reduces the time and energy of the end user on data ingestion. 2) Data ingestion is done by hadoop ecosystem 3) Metadata extraction and data type conversion
Key Achievements and Challenges in the Last Month
Accomplished: Scheduling of jobs using Cron - 4-April-2016(completed) MetaData extraction - 11-April-2016(completed) Evaluating the data type matching in hexaconnect- 18-April-2016(completed) working for oracle database connection in hexaconnect - 25-April-2016(completed) Challenges: Generation of the script and testing it in the environment Interaction of java with the hadoop environment.
Project Execution
Training Needs | Training for Java/.Net | <mention the pending needs and challenges if any>
Critical Risks | No Risks Identified so far | <Refer critical risks from PP>
Critical Issues | None | <Refer critical issues from PP / WSR>
Open RR's | Nil | Nil
Review by Competency | Ranganathan Rajkumar | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | Nil | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Finalization of the First model which is to be implemented |  |  |  |  | 2016-04-04 | 2016-01-04 | Completed
Adding new databases |  |  |  |  | TBD | TBD | WIP
Final Version of the Product |  |  |  |  | TBD | TBD | WIP
Testing and corrections |  |  |  |  | TBD | TBD | Yet to Start
Started executing shell scripts from web application and moving BLOB and CLOB.
Project Health Card
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization % |  | 100
Risks | All Risks are within control |  | Consultant Utilization % |  | 100
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Yet to be requested
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Thangarajan | Developer | G3 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG
RajKumar |  | G2 | 100 | 2016-03-01 | 2016-12-31 | OEG | Relese date as per the RMG

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 1 | 50%
G3 | 6 | G3 | 1 | 50%
G5 | 1
G6 | 2
G7 | 1
G8 | 2
G4 | 3
Grand Total | 16