## MonthlyProjectStatus
BIBA Metadata Accelerators Offering Monthly Status Report - April 2016
Project Details
Project ID | PRJ-4656
Project Name | BIBA - Soultion - BI Metadata_Accelerators
Project Type | Maintenance
Project Manager | Murugesh Pandian Meenapandi
Offerings / Unit | BIBA Service Offering
Offering Owner | Murugesh Pandian Meenapandi
Project Start Date | 2016-02-01
Project End Date | 2016-12-31
Tech Finance ID | 92517
Project Description
Soltution for Metadata management and migration automation for various report and ETL tools. BIMA, DIMA, DART, INFAGEN, SQL PARSER, RLA , SLA, FIRE helps variours customer to capture metadata and doing automation of impact analysis & migraions.
Key Achievements and Challenges in the Last Month
Accomplished: RLA BO 4.1 -Solved issues in taking the particular data provider(Query) column - 4/4/2016 Completed RLA BO 4.1(dbcognos Macro)-Creating macro for changing dataitem name as database field name (due to label name issue) and update field name in pagedetails,Reportitem tables- 4/5/2016Completed Catalent report Export and Metadata Extraction - 4/5/2016 Completed Creating Setup File for FIRE Tool - 4/6/2016 Completed BO to SSRS demo(BNP)- 4/6/2016 Completed Informtica TDM - 4/7/2016Completed SLA Bo 4.1 development-Created Sample connection(cnx) file in local folder - 4/12/2016 Completed SLA Bo 4.1 development-Created Sample Datafoundation(dfx) file in local folder - 4/13/2016 Completed BO universe to SSAS Tabular model-created simple model for single universe - 4/14/2016 Completed Developed Complexity report for BIMA for MSTR-4/15/2016 Completed Demo for Hermes (BIMA WEBI) - 4/5/2016 Completed ETL Informatica Job Failure Data Analysis - 4/12/2016 Completed Metadata analysis Report for MSTR- 4/22/2016 Completed BO to SSRS Enhancements(RLA-Crosstab with summary field) - 4/22/2016 Completed BO Universe to SSAS Tabular Model-Multiple universe and joins - 4/21/2016 Completed BO to SSRS demo to BNP (Training) - 4/20/2016 Completed Demo for BIMA,DART,SQL Parser - 4/25/2016 Completed Extraction of Catalent reports -Phase1 - 4/27/2016 Completed SLA for SSAS -joins,Front end,Report creation using tabular model- 4/28/2016 Completed BIMA for MSTR-Getting Report type in Selected Report Table -4/26/2016 Completed BO Universe to SSAS Tabular Model-Multiple universe and joins - 4/21/2016 Completed BIMA for MSTR-Metrics table (duplicate issue),Report table information - 4/27/2016 Completed
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Catalent Report Migration-phase2 |  |  |  |  | 2016-05-15 | 2016-05-15 | WIP
Enhancements in RLA for BO 4.1-Test the tool with latest version of BO |  |  |  |  | 2016-05-31 | 2016-05-31 | WIP
BIMA for universe(BO 4.1) |  |  |  |  | 2016-05-31 | 2016-05-31 | WIP
Cognos Framework to BO Universe (SLA Tool Creation) |  |  |  |  | 2016-05-31 | 2016-05-31 | WIP
BO to SSRS deployment in BNP |  |  |  |  | 2016-05-15 | 2016-05-15 | Yet to start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is on track |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks | All Risks are within control |  | Consultant Utilization %
Issues | Project issues need attention |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested
Software / Hardware Availed |  | Hardware: 64 Bit Cloud servers Softwares: .Net 3.5 or above, Java JDK & JRE 1.7 or above, Eclipse, Visual Studio 2008 & 2013, SQL server 2008 & 2012, Apache Tomcat 6 or above, JBOSS Open Source Frameworks & Softwares: .Net Framework 3.5 or above, Java JDK & JRE 1.7 or above.

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
Parkavi P | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Usha Gomathi M | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Deepak Kumar K | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Revathi K | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Rahimuddin Mohammed | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA
Imran | TM | G3 | 100 | 2016-02-02 | 2016-12-31 | Competency Dev-BIBA

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G3 | 6 | G2 | 0 | 0%
Grand Total | 6 | G3 | 5 | 100%
|  | G4 | 0 | 0%
|  | G5 | 0 | 0%
|  | G6 | 0 | 0%
|  | G7 | 0 | 0%
|  | G8 | 0 | 0%
|  | >G8 |  | 0%