## MonthlyProjectStatus
CRES Offering Status Report - March 2016
Project Details
Project ID | PRJ-4660 - OEG_BFS_CRES Works
Project Name | CRES Offering
Project Type | Development
Project Manager
Offerings / Unit | Workstation Utilization
Offering Owner | Alok Mishra
Project Start Date | 2016-03-10
Project End Date | 2016-05-31
Tech Finance ID
Project Description
CRES Service Offering is a solution to measure the utilization of seats, meeting room and board room facilities in percentage. 1) Accurately captures the seats utilised BU/floor/duilding/site/location/country/region wise. 2) Utilization of seats can be compared with the previous period. 3) User level access screen like Executive and Admin Dashboard.
Key Achievements and Challenges in the Last Month
Accomplished: Executive Dashboard completed Allocation completed in Executive Dashboard Admin Console Completed Challenges:
Project Execution
Training Needs | <any training pending> | <mention the pending needs and challenges if any>
Critical Risks | <Count of open risks> | <Refer critical risks from PP>
Critical Issues | <Count of open issues> | <Refer critical issues from PP / WSR>
Open RR's
Review by Competency | <Review conducted in reporting period> | <Plan for next month>
PHI | Target <>, Actuals <>
Open NC / Observations of IQA | <Count of NC> and <Audit Score> | <Refer IQA Tool>
Project MileStones |  |  |  |  | Target Date | Expected Completion Date | Status
Executive Dashboard |  |  |  |  | 2016-04-22 | 2016-04-22 | Completed
Executive Dashboard Review and Allocation completed |  |  |  |  | 2016-04-22 | 2016-04-22 | Completed
Admin Dashboard Development completed |  |  |  |  | 2016-04-26 | 2016-04-26 | Completed
Lease and Payment development started |  |  |  |  | 2016-04-26 | 2016-05-11 | WIP
Testing |  |  |  |  | 2016-05-18 | 2016-05-18 | Yet to Start
Project Health Card |  |  | Metrics
Schedule | The Project schedule is extended |  | Schedule Variance
Resourcing | Resourcing is adequate |  | Effort Utilization %
Risks |  |  | Consultant Utilization %
Issues |  |  | Number of post shipment defects
|  |  | Severity | Critical <count> | High <count> | Medium <count> | Low <count>
Software / Hardware Licensing
Software / Hardware Requested |  | Tableau Desktop and Server Environment was purchased
Software / Hardware Availed

## ConsultantMatrix
<Can be taken by the PM from RMG>
Name | Role | Grade | % Allocated | Consultant Start Date | Consultant Release Date | Owning Unit | Remarks
G3
G3
G3
G3
G3
G3
G2
G5
G6
G6
G7
G8
G8
G4
G4
G4

## Pivot
Row Labels | Count of Grade | Grade | No. of consultant | % of Total FTE
G2 | 1 | G2 | 0 | 0%
G3 | 6 | G3 | 0 | 0%
G5 | 1 | G4 | 0 | 0%
G6 | 2 | G5 | 2 | 100%
G7 | 1 | G6 | 0 | 0%
G8 | 2 | G7 | 0 | 0%
G4 | 3 | G8 | 0 | 0%
Grand Total | 16 | >G8 |  | 0%